## Sheet1
Plan | [8 empty] | Up-to-date Actuality
Task | [5 empty] | Business Time |  |  | Task
Name | Description | Resource |  | Deliverable | Directly Report To | Starting Date | Ending Date | Working Time | Status | Deliverable | Resource
|  | Time | Others | [7 empty] | Time | Others
AutoUpdatePiSG | a program that add self-update feature to the project | raw flow chart: 8h raw code: 8h raw test + revise: 24h installer code: 8h document: 8h tolerance:8h |  | _Code + Deployable Program + Installer + Document | Tâm |  |  | 64h | completed before Jun | _Code + Deployable Program + Installer + Document | 70h
UHV2Worker | a thread that communicate with UHV2 pump, based on BinaryProtocol via RS485 Serial Interface | FSM model design: 20h effective threading techniques: 8h raw state diagram: 7h raw code: 7h raw test + revise: 11h tolerance: 5h |  | _Code + Diagram | Tâm | 2017-06-05 |  | 58h | completed on 6/14 | _Code + Diagram | FSM design: 27h Threading: 10h State Diagram + Code + Test + Revise: 17h
CanBusWorker | a thread that communicate with Can bus, based on CanProtocol | raw state diagram: 7h raw code: 8h raw test + revise: 5h tolerance: 5h |  | _Code + Diagram | Tâm | 2017-06-15 |  | 25h | completed on 6/21 | _Code + Diagram | State Diagram + Code + Test + Revise: 34h
anLogger | a macro that supports very detailed debug and writes log file, on both WinOS and LinuxOS | logic design: 8h raw code: 5h raw test + revise: 7h tolerance: 5h |  | _Code | Tâm | 2017-06-22 |  | 25h | completed on 6/27 | _Code | Code + Test + Revise: 31h
[8 empty] | 172h |  |  | 189h
piLocalDBWorker | a thread that provides write/read functions with local database on pi | learn and test qsql: 8h work with Đăng : 8h meeting with team: 6h raw state diagram: 5h raw code: 5h raw test + revise: 5h tolerance: 5h | Tâm: 6h Đăng: 14h Đăng code Đăng database | _Basic Function: Initialize/Write/Read _Code + Diagram | Tâm |  |  | 42h | wait for approval
Auto UHV2 PVI Collector | a thread collecting PVI of UHV2 and put into database | raw state diagram: 3h raw code: 3h raw test + revise: 3h tolerance: 5h |  | _Code + Diagram | Tâm |  |  | 20h | wait for approval
Auto UHV4 PVI Collector | a thread collecting PVI of UHV4 and put into database | raw state diagram: 1h raw code: 1h raw test + revise: 1h tolerance: 3h |  | _Code + Diagram | Tâm |  |  | 5h | wait for approval
Auto CAN Data Collector | a thread collecting RFID and put into database | meeting with Tâm: 3h raw state diagram: 3h raw code: 3h raw test + revise: 3h tolerance: 5h | Tâm: 3h | _Code + Diagram | Tâm |  |  | 17h | wait for approval
Small Coordinator | a thread directing the data | meeting with Tâm: 5h raw state diagram: 5h raw code: 5h raw test + revise: 8h tolerance: 8h | Tâm: 5h | _Code + Diagram | Tâm |  |  | 31h | wait for approval
Combination | refractor and revise code, to make all things work in harmony | raw work: 5h test + revise: 5h tolerance:8h |  | _Code + Diagram | Tâm |  |  | 18h | wait for approval
TestGui | a thread that allows test and debug | raw code: 5h tolerance: 5h |  | _Code | Tâm |  |  | 10h | wait for approval
Excel Debugger | an excel log analysing program activities | raw flow chart: 8h raw code: 8h raw test + revise: 5h tolerance: 5h |  | _Code + Example | Tâm |  |  | 26h | wait for approval
Big Test + Fix Bug | all kind of functions will be test | meeting with Tâm: 1h raw work: 5h tolerance: 5h | Tâm: 1h | _Code + Accessment | Tâm |  |  | 11h | wait for approval
Realization | test and debug with simulators | intensive test and debug with Đăng: 8h team meeting: 2h tolerance: 10h | Tâm: 2h Đăng: 8h 12 x UHV2Simulators 12 x UHV4Simulators 6 x SDCSFullSimulators VPS | _Deployable Program | Tâm |  |  | 20h | wait for approval
EDCTU Software |  | 200h | Tâm: 17h Đăng: 22h |  | Tâm |  |  | 200h | wait for approval