## Sheet1
Plan | [8 empty] | Up-to-date Actuality
Task | [5 empty] | Business Time |  |  | Task
Name | Description | Resource |  | Deliverable | Directly Report To | Starting Date | Ending Date | Working Time | Status | Deliverable | Resource
|  | Time | Others | [7 empty] | Time | Others
piLocalDBWorker | a thread that provides write/read functions with local database on pi | learn and test qsql: 8h meeting with team: 3h raw state diagram: 5h raw code: 5h raw test + revise: 5h tolerance: 5h | Tâm: 3h Đăng: 3h Đăng code Đăng database | _Basic Function: Initialize/Write/Read _Code + Diagram | Tâm |  |  | 31h | wait for approval
Online VPS2 DB Communicator | a thread that provides write/read functions with online database VPS2 | work with Đăng: 8h meeting with team: 3h raw state diagram: 5h raw code: 5h raw test + revise: 5h tolerance: 5h | Tâm: 3h Đăng: 11h Đăng code | _Basic Function: Write/Read _Code + Diagram | Tâm |  |  | 31h | wait for approval
Auto UHV2 PVI Collector | a thread collecting PVI of UHV2 and put into database | raw state diagram: 3h raw code: 3h raw test + revise: 3h tolerance: 5h |  | _Code + Diagram | Tâm |  |  | 20h | wait for approval
Auto UHV4 PVI Collector | a thread collecting PVI of UHV4 and put into database | raw state diagram: 1h raw code: 1h raw test + revise: 1h tolerance: 3h |  | _Code + Diagram | Tâm |  |  | 5h | wait for approval
Auto CAN Data Collector | a thread collecting RFID and put into database | meeting with Tâm: 3h raw state diagram: 3h raw code: 3h raw test + revise: 3h tolerance: 5h | Tâm: 3h | _Code + Diagram | Tâm |  |  | 17h | wait for approval
Small Coordinator | a thread directing the data | meeting with Tâm: 5h raw state diagram: 5h raw code: 5h raw test + revise: 8h tolerance: 8h | Tâm: 5h | _Code + Diagram | Tâm |  |  | 31h | wait for approval
Combination | refractor and revise code, to make all things work in harmony | raw work: 5h test + revise: 5h tolerance:8h |  | _Code + Diagram | Tâm |  |  | 18h | wait for approval
Logger | an excel log recording program activities at running time | raw flow chart: 8h raw code: 8h raw test + revise: 5h tolerance: 5h |  | _Code + Example | Tâm |  |  | 26h | wait for approval
Big Test + Fix Bug | all kind of functions will be test | meeting with Tâm: 1h raw work: 10h tolerance: 10h | Tâm: 1h | _Code + Accessment | Tâm |  |  | 21h | wait for approval
EDCTU Software |  | 200h | Tâm: 15h Đăng: 14h |  | Tâm |  |  | 200h | wait for approval